{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["問題資料20171027133513"],"not_rendered":{"charts":0,"images":1,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"問題資料20171027133513","index":0,"n_rows":48,"n_cols":11,"rows_kept":48,"cut":false,"hidden":false,"merged":[[0,0,0,11],[1,0,1,11]]}
["問題資料"]
["匯出時間:2017/10/27"]
["項次","編號","議題類別","重要程度","狀態","摘要","提出人/時間","討論次數/最後回覆人","被指派人","修復者","預計日期"]
[1,147,"使用性調整","高","新問題","作廢刪除不能只針對帳單","奕達運通有限公司(林筱甄) / 2017/10/26","0 / 林筱甄","原玉東"]
[2,146,"程式錯誤","高","新問題","「客戶管理」審核功能異常","奕達運通有限公司(黃淑梅) / 2017/10/26","0 / 黃淑梅","原玉東"]
[3,145,"使用性調整","中","新問題","「展覽管理」及「客戶管理」查詢頁面資料排序","奕達運通有限公司(黃淑梅) / 2017/10/26","0 / 黃淑梅","原玉東"]
[4,144,"程式錯誤","高","新問題","進口「退運」小日曆無法操作","奕達運通有限公司(黃淑梅) / 2017/10/26","0 / 黃淑梅","原玉東"]
[5,120,"新需求","高","已處理","帳單「預收」部份，當帳單一成立就請開放讓會計填寫","奕達運通有限公司(林筱甄) / 2017/10/16","2 / 林筱甄","原玉東"]
[6,143,"使用性調整","高","新問題","「展覽管理」使用性調整","奕達運通有限公司(黃淑梅) / 2017/10/25","0 / 黃淑梅","原玉東"]
[7,142,"程式錯誤","高","新問題","前台「貨況追蹤」客戶名刪除「簡稱」","奕達運通有限公司(黃淑梅) / 2017/10/25","0 / 黃淑梅","原玉東"]
[8,141,"程式錯誤","高","新問題","出口多廠商流程問題","奕達運通有限公司(黃淑梅) / 2017/10/25","0 / 黃淑梅","原玉東"]
[9,140,"使用性調整","中","新問題","出口「多廠商列表」排序調整","奕達運通有限公司(黃淑梅) / 2017/10/25","0 / 黃淑梅","原玉東"]
[10,139,null,"請選擇...","新問題","「展覽名稱」搜尋結果改成「（簡稱）＋全名」","奕達運通有限公司(黃淑梅) / 2017/10/25","0 / 黃淑梅"]
[11,138,null,"請選擇...","新問題","客戶管理「狀態」選無效須加填原因","奕達運通有限公司(黃淑梅) / 2017/10/25","0 / 黃淑梅"]
[12,137,"使用性調整","高","新問題","創建者也可新增報價","奕達運通有限公司(林筱甄) / 2017/10/25","0 / 林筱甄","原玉東"]
[13,135,"新需求","高","新問題","「客戶管理」新增欄位限制","奕達運通有限公司(黃淑梅) / 2017/10/24","1 / 黃淑梅","原玉東"]
[14,136,"使用性調整","中","新問題","帳單格式修改","奕達運通有限公司(林筱甄) / 2017/10/24","0 / 林筱甄","原玉東"]
[15,134,"使用性調整","低","新問題","「客戶管理」被退件-放到業務端「待處理事項」","奕達運通有限公司(黃淑梅) / 2017/10/24","1 / 黃淑梅","原玉東"]
[16,133,"其他","極低","新問題","「個人主頁」規劃","奕達運通有限公司(黃淑梅) / 2017/10/24","0 / 黃淑梅","原玉東"]
[17,117,"程式錯誤","高","已處理","進口滙入功能異常","奕達運通有限公司(黃淑梅) / 2017/10/13","4 / 黃淑梅","原玉東"]
[18,123,"新需求","中","已處理","「展覽管理」3語系「國別」「地點(展館)」資料建置","奕達運通有限公司(黃淑梅) / 2017/10/17","2 / 黃淑梅","原玉東"]
[19,128,"使用性調整","中","已處理","「貨櫃號碼」欄位調整","奕達運通有限公司(黃淑梅) / 2017/10/18","2 / 原玉東","黃淑梅"]
[20,131,"使用性調整","高","新問題","「已作廢」資料帳單處理方式","奕達運通有限公司(黃淑梅) / 2017/10/19","0 / 黃淑梅","原玉東"]
[21,130,"使用性調整","高","新問題","所有涉及「客戶管理」資料庫之欄位顯示方法","奕達運通有限公司(黃淑梅) / 2017/10/19","0 / 黃淑梅","原玉東"]
[22,119,"新需求","高","已處理","「報價」及「預估成本」改為上下並排","奕達運通有限公司(林筱甄) / 2017/10/16","1 / 原玉東","林筱甄"]
[23,129,"使用性調整","中","新問題","出口多廠商「退運」操作方式調整","奕達運通有限公司(黃淑梅) / 2017/10/18","1 / 原玉東","黃淑梅"]
[24,126,"新需求","中","已處理","帳單新增「聯絡人」及「聯絡電話」欄位","奕達運通有限公司(林筱甄) / 2017/10/17","1 / 原玉東","林筱甄"]
[25,125,"使用性調整","低","新問題","進口「保稅資料」頁籤欄位調整","奕達運通有限公司(黃淑梅) / 2017/10/17","0 / 黃淑梅","原玉東"]
[26,124,"使用性調整","低","新問題","出口流程刪除「航行中」欄位","奕達運通有限公司(黃淑梅) / 2017/10/17","0 / 黃淑梅","原玉東"]
[27,122,"使用性調整","低","新問題","進出口「基本資料」欄位調整","奕達運通有限公司(黃淑梅) / 2017/10/16","1 / 黃淑梅","原玉東"]
[28,111,"使用性調整","低","處理中","「公告管理」調整","奕達運通有限公司(黃淑梅) / 2017/10/12","7 / 黃淑梅","原玉東"]
[29,112,"使用性調整","中","已處理","新增「備註」欄位，並鎖定「費用說明」欄位不可修改","奕達運通有限公司(林筱甄) / 2017/10/12","1 / 原玉東","林筱甄"]
[30,108,"程式錯誤","中","已處理","帳單付款人選擇後，無法回寫入系統顯現","奕達運通有限公司(林筱甄) / 2017/10/06","1 / 原玉東","林筱甄"]
[31,107,"程式錯誤","低","已處理","費用代碼若有「-」，會顯示異常","奕達運通有限公司(林筱甄) / 2017/10/06","1 / 原玉東","林筱甄"]
[32,110,"新需求","中","已處理","預估報價/成本中的成本也能使用「匯入」功能","奕達運通有限公司(林筱甄) / 2017/10/11","1 / 原玉東","林筱甄"]
[33,109,"程式錯誤","極高","已處理","測試結果，帳單資料無法轉入文中","奕達運通有限公司(林筱甄) / 2017/10/06","1 / 原玉東","林筱甄"]
[34,96,"新需求","低","已處理","所有退運情形的帳單皆在「退運報價/預估成本」建立","奕達運通有限公司(林筱甄) / 2017/09/19","3 / 原玉東","林筱甄"]
[35,100,"使用性調整","極低","已處理","「查詢號碼寄送email」欄位開放可填多筆","奕達運通有限公司(黃淑梅) / 2017/09/21","2 / 原玉東","黃淑梅"]
[36,97,"新需求","低","已處理","報價/預估成本以EXCEL方式匯入","奕達運通有限公司(林筱甄) / 2017/09/19","1 / 原玉東","林筱甄"]
[37,98,"使用性調整","低","已處理","發票、收據鎖定邏輯","奕達運通有限公司(林筱甄) / 2017/09/20","1 / 原玉東","林筱甄"]
[38,99,"使用性調整","低","已處理","帳單付款人選取方式需修改","奕達運通有限公司(林筱甄) / 2017/09/20","1 / 原玉東","林筱甄"]
[39,95,"新需求","中","已處理","出口「查詢頁面」增加「貨物狀態」欄位","奕達運通有限公司(黃淑梅) / 2017/09/12","2 / 黃淑梅","原玉東"]
[40,90,"程式錯誤","高","已處理","出口多廠商「批次操作」沒作用等問題","奕達運通有限公司(黃淑梅) / 2017/08/09","3 / 原玉東","黃淑梅"]
[41,60,"新需求","中","已處理","後台優化及整併","奕達運通有限公司(黃淑梅) / 2017/06/12","3 / 黃淑梅","原玉東"]
[42,83,"新需求","低","已處理","新增「展覽管理」資料庫","奕達運通有限公司(黃淑梅) / 2017/07/21","2 / 黃淑梅","原玉東"]
[43,85,"新需求","中","已處理","「一般進出口」併入「展品進出口」等需求","奕達運通有限公司(黃淑梅) / 2017/07/25","2 / 黃淑梅","原玉東"]
[44,19,"新需求","高","已處理","出口作業流程","奕達運通有限公司(黃淑梅) / 2017/03/21","14 / 原玉東","黃淑梅"]
[45,61,"新需求","低","新問題","「客戶管理」載入政府open data","奕達運通有限公司(黃淑梅) / 2017/06/12","0 / 黃淑梅","原玉東"]