{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["資訊時程","時程摘要"],"not_rendered":{"charts":0,"images":1,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"資訊時程","index":0,"n_rows":50,"n_cols":345,"rows_kept":50,"cut":false,"hidden":false,"merged":[[51,1,51,7],[11,0,15,0],[38,0,38,7],[25,0,25,7],[16,0,21,0],[40,0,44,0],[27,0,32,0],[0,7,1,7],[0,6,1,6],[0,5,1,5],[0,4,1,4],[3,0,8,0]]}
[{"$nulls":4},"日曆天","周","擔當","地點",1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,1,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,2,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,3,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,4,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,5,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,6,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,8,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,9,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,10,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,11,12,12,12]
["階段","預定開始","預訂結束",{"$nulls":5},1,{"$f":"I2+1","v":2},{"$f":"J2+1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,1,{"$f":"AN2+1","v":2},{"$f":"AO2+1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,1,{"$f":"BP2+1","v":2},{"$f":"BQ2+1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,1,{"$f":"CU2+1","v":2},{"$f":"CV2+1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,1,{"$f":"DY2+1","v":2},{"$f":"DZ2+1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,1,{"$f":"FD2+1","v":2},{"$f":"FE2+1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,1,{"$f":"GH2+1","v":2},{"$f":"GI2+1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,1,{"$f":"HM2+1","v":2},{"$f":"HN2+1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,1,{"$f":"IR2+1","v":2},{"$f":"IS2+1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,1,{"$f":"JV2+1","v":2},{"$f":"JW2+1","v":3},4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,{"$f":"1","v":1},{"$f":"LA2+1","v":2},{"$f":"LB2+1","v":3},{"$f":"LC2+1","v":4},{"$f":"LD2+1","v":5},{"$f":"LE2+1","v":6},{"$f":"LF2+1","v":7},{"$f":"LG2+1","v":8},{"$f":"LH2+1","v":9},{"$f":"LI2+1","v":10},{"$f":"LJ2+1","v":11},{"$f":"LK2+1","v":12},{"$f":"LL2+1","v":13},{"$f":"LM2+1","v":14},{"$f":"LN2+1","v":15},{"$f":"LO2+1","v":16},{"$f":"LP2+1","v":17},{"$f":"LQ2+1","v":18},{"$f":"LR2+1","v":19},{"$f":"LS2+1","v":20},{"$f":"LT2+1","v":21},{"$f":"LU2+1","v":22},{"$f":"LV2+1","v":23},{"$f":"LW2+1","v":24},{"$f":"LX2+1","v":25},{"$f":"LY2+1","v":26},{"$f":"LZ2+1","v":27},{"$f":"MA2+1","v":28},{"$f":"MB2+1","v":29},{"$f":"MC2+1","v":30},1,{"$f":"ME2+1","v":2},{"$f":"MF2+1","v":3}]
["URD by Function","2023-01-10","2023-03-11","Can be partially released by separable function"]
["系統設計","~","2023-01-20","IP address初版規劃",null,null,"tsmc","Net Meeting"]
[null,"~","2023-01-20","完成作業需求、系統功能需求、Data Flow確認",null,null,"tsmc","Net Meeting"]
[null,null,"2023-02-15","完成web Service架構、內容確認",null,null,"tsmc","Net Meeting"]
[null,null," 2023/2/28","fire wall搞定",null,null,"tsmc"]
[null,"2023-01-30","2023-03-03","完成數據庫設計",{"$f":"C8-B8+1","v":33},5,"D0,D1","新竹Mirle"]
[null,null,"2023-03-11","完成所有URD確認",null,null,"tsmc","Net Meeting"]
["Development & System Testing(ST)","2023-01-10","2023-07-02","user provide off-line simulation data"]
["Web Service程式設計與開發","2023-02-20","2023-03-31","Web Service接口開發完成",{"$f":"C11-B11+1","v":40},6,"C1,T1","新竹Mirle"]
["WES程式\n設計與開發","2023-01-10","2023-06-02","完成維護作業程式&測試(16)",144,18,"C1,C2,T1","新竹Mirle"]
[null,"2023-01-10","2023-06-02","完成入庫作業程式&庫位移轉作業程式&測試(10)",144,18,"C2,T1","新竹Mirle"]
[null,"2023-01-10","2023-06-02","完成出庫作業程式&測試(10)",144,18,"C3,T1","新竹Mirle"]
[null,"2023-06-05","2023-07-02","完成查詢作業程式(17)",28,6,"C1,C4,T1","新竹Mirle"]
[null,"2023-06-05","2023-07-02","完成報表作業程式(14)",28,6,"C2,C3,T1","新竹Mirle"]
["WCS程式\n設計與開發","2023-01-30","2023-02-24","WCS與電控PLC通訊協議確認完成",26,4,"C4","上海Mirle"]
[null,"2023-02-27","2023-05-05","WCS(乙倉1)開發完成",{"$f":"C18-B18+1","v":68},10,"C4","上海Mirle"]
[null,"2023-05-08","2023-06-09","完成WCS(乙倉1)程式功能模擬測試",33,5,"C4,T2","上海Mirle"]
[null,"2023-05-08","2023-06-25","WCS(乙倉2)開發完成",49,8,"C5","上海Mirle"]
[null,"2023-06-10","2023-06-30","Auto-Run控制程式開發",21,3,"C4,T2","上海Mirle"]
[null,"2023-06-26","2023-07-02","完成WCS(乙倉2)程式功能模擬測試",7,3,"C5,T3","上海Mirle"]
["User Testing(UT)","2023-07-03","2023-07-14","user provide off-line test data and barcode label",{"$f":"C23-B23+1","v":12},6,"C1,T1","新竹Mirle"]
["System Integration Testing(SIT)","2023-07-11","2023-09-11","IT provide on-line testing data for ASRS testing enviroment",63,4,"C1,T1","乙倉1"]
["User Acceptance Testing(UAT)","2023-07-11","2023-09-11","User on-line testing data for IT & ASRS software",63,3,null,"乙倉1 & 2"]
["乙倉1"]
["Hardware Installation","2023-05-08","2023-06-16",null,{"$f":"C27-B27+1","v":40},8]
["乙倉1現場安裝作業","2023-05-08","2023-05-14","CV定位",{"$f":"C28-B28+1","v":7},1,null,"乙倉1"]
[null,"2023-05-15","2023-05-29","網路完成佈線(乙倉1)",15,2,null,"乙倉1"]
[null,null,"2023-05-30","送電(乙倉1)",null,null,null,"乙倉1"]
[null,"2023-05-29","2023-06-16","完成乙倉1 Oracle Server安裝",{"$f":"C31-B31+1","v":19},2,null,"乙倉1"]
[null,"2023-05-30","2023-06-04","完成乙倉1 Control PC(WCS Server)安裝",6,1,null,"乙倉1"]
[null,"2023-06-05","2023-06-11","完成乙倉1 WorkstationPC安裝",7,1,null,"乙倉1"]
["Equipment Single Test","2023-06-13","2023-06-19","半自動測試(設備Function Test)",{"$f":"C34-B34+1","v":7},1]
["Equipment Integration Test","2023-06-17","2023-08-01","include other connected equipment(ex. FAC DHL)\n(含WCS & tsmc Web Service Interface)",{"$f":"C35-B35+1","v":46},7,"C4,T2","乙倉1"]
["Function Testing\n(72hrs non-stopping test)","2023-08-02","2023-08-04","exclude other connected equipment\n(Auto-Run連續測試)",{"$f":"C36-B36+1","v":3},1,"C4,T2","乙倉1"]
["Software & Hardware Integration Testing","2023-09-18","2023-09-22","全系統整合測試(含tsmc Web Service Interface)",{"$f":"C37-B37+1","v":5},2,"C1,C4,T2","乙倉1"]
["Production Release and Babysitting Review","2023-10-02","2023-11-26","8周穩定度測試",{"$f":"C38-B38+1","v":56},8,"C1,C4,T2","乙倉1"]
["乙倉2 "]
["Hardware Installation","2023-06-22","2023-07-23",null,{"$f":"C40-B40+1","v":32},5]
["乙倉2現場安裝作業","2023-06-22","2023-06-29","CV定位",{"$f":"C41-B41+1","v":8},1,null,"乙倉2"]
[null,"2023-06-30","2023-07-14","網路完成佈線(乙倉2)",15,2,null,"乙倉2"]
[null,null,"2023-07-08","送電(乙倉2)",null,null,null,"乙倉2"]
[null,"2023-07-10","2023-07-16","完成乙倉2 Control PC(WCS Server)安裝",7,1,null,"乙倉2"]
[null,"2023-07-17","2023-07-23","完成乙倉2 WorkstationPC安裝",7,1,null,"乙倉2"]
["Equipment Single Test","2023-07-24","2023-07-30","半自動測試(設備Function Test)",7,1,null,"乙倉2"]
["Equipment Integration Test","2023-07-28","2023-09-11","include other connected equipment(ex. FAC DHL)\n(含WCS & tsmc Web Service Interface)",46,7,"C5,T3","乙倉2"]
["Function Testing\n(72hrs non-stopping test)","2023-09-12","2023-09-14","exclude other connected equipment\n(Auto-Run連續測試)",{"$f":"C48-B48+1","v":3},1,"C5,T3","乙倉2"]
["Software & Hardware Integration Testing","2023-09-18","2023-09-22","全系統整合測試(含tsmc Web Service Interface)",{"$f":"C49-B49+1","v":5},1,"C1,C5,T3","乙倉1"]
["Production Release and Babysitting Review","2023-10-09","2023-12-03","8周穩定度測試",56,9,"C1,C5,T3","乙倉1"]

{"sheet":"時程摘要","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}